## Master
Goal: to add minimum of $350,000 of gross business to the Pipeline by the end of 90 days
Goal 2: Building a Sales Methodology and where to apply it
Goal 3:Building Sales Initiatives and an Approach Methodology
Core Objectives:
Objective 1: | Establish Pipeline & Critical Path
Objective 2: | Pre-Pipeline Prospecting Skills
Objective 3: | Scrubber SkillSets - prospect identification toolsets
Objective 4: | ToolSets and Solution Providers
Objective 5: | Case Support and Communication
Key Events |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
Assigned Date Schedule | owner | team members
Establish Pipeline & Critical Path | Greg | Greg/David
Review of Pipeline & Adjustments | bar: Week 1 to Week 2
Review of Supporting tool kit & Provision gaps | bar: Week 2 to Week 3
Building a Sales Methodology | bar: Week 1 to Week 2
Capabilities Presentation | bar: Week 3 to Week 4
Marketing Presentation Formats for H&W | bar: Week 3 to Week 6
Report Pipeline
Pre-Pipeline Prospecting Skills | Greg | Greg/David
Building Sales Initiatives | bar: Week 3 to Week 5; Week 8
LinkedIn (profile/contacts/endorsements/research) | bar: Week 3 to Week 6
Strategic Alliance/COI Development | bar: Week 5 to Week 6
Blunders and Breakthroughs | bar: Week 5 to Week 6
Introductions & Referrals | bar: Week 7 to Week 8
Packaging the Approach | bar: Week 6
the JoyPAK | bar: Week 3 to Week 5; Week 9 to Week 10
Scrubber SkillSets - prospect ID Toolsets | Greg | Greg/David
Research | bar: Week 5 to Week 6
Identifying "Imperfections of Fit' | bar: Week 1 to Week 2
Competitor Intelligence - gathering and evaluating | bar: Week 4 to Week 6
ToolSets and Solution Providers | David | David/Greg/SP's
Examine and Provision ToolSets
Health Care reform toolset distribution (CHRS) | bar: Week 3 to Week 5
Case Support & Communication | Greg | Greg/David
One-on-One
Introductions to Solution Providers & Affiliates
Key event/webinar invitations
Pipeline & Activity Metric Reporting | Greg | Greg/David
Pipeline Report - Goal | Greg |  | Week 2: 50000; Week 4: 150000; Week 6: 200000; Week 8: 250000; Week 10: 300000; Week 12: 350000
Pipeline Report - Actual
New Business Appointments - Goal | Greg |  |  |  | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2
New Business Appointments - Actual
Top 25 Prospect List - Goal | Greg |  |  | 10 | 20 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
Top 25 Prospect List - Actual
SAP Developed (Individual) - Goal | Greg | bar: Week 4; Week 6; Week 8; Week 10; Week 12
SAP Developed (Individual) - Actual
Introductions Obtained - Goal | Greg |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Introductions Obtained - Actual
LinkedIn Connections Added - Goal | Greg |  |  |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
LinkedIn Connections Added - Actual